Sustainable Respiratory Care Advisory Group

Sustainable Inhalers Programme

Summary table of actions from telephone meetings 4th Feb 2013 and 15th Feb 2013

| Objective | Actions | Notes |
| --- | --- | --- |
| Prepare briefing note for use in development phase (including input to NHS Sustainable Development Strategy consultation) | Adv Grp to review & input to draft briefing | By 8 March |
| Put together the economic argument, e.g., a cost-benefit analysis for inhaler switch coupled with reduction in unnecessary prescribing |  | LSE (already working on this with Impress)* |
| Understand process by which prices are set between NHS and industry and how this could be influenced |  |  |
| Research patient attitudes & barriers to change (inc. audience segmentation) | Will Nattrass with CSH: literature review then patient survey design |  |
| Develop & test messages (audience, content, media) | Nick Hopkinson investigating trial of messages to GPs. Noel Baxter offering input. |  |
| Engage strategic groups: pharmacists, DH | CSH to follow up on introduction to Keith Ridge (DH pharmacy lead) |  |
| Secure funding for programme development phase | CSH developing proposal & approaching funders |  |
| Coordinate efforts | All to share resources and communicate progress via online network* |  |
| Convene Programme Board | CSH – once development phase funding in place |  |

* Mara Airoldi at LSE is leading on the Impress collaboration. She is working on this with Chiara De-Poli

* http://sustainablehealthcare.org.uk/sustainable-respiratory-care (please contact Frances frances.mortimer@sustainablehealthcare.org.uk if help needed in using the online network)